## Event Buget
ITEM | Budget Amount
Venue Rental
Advertising Costs:Facebook Ads, Print Materials
Event Rentals: Tables, Chairs, Linens
Entertainment
Food
Beverages
Décor
Travel Costs
Miscelaneous Expenses
Total

## Event Details
DETAILS:
Type of Event
Date of Event
Time
Location of Event
Number of expected Guests
Theme:
Colour
Style
Overall feeling
Entertainment:
Guest Speakers
DJ or Band
Sound Equipment
Games and Activities
Catering Requirments
Food
Beverages
Snacks
Event Requirments:
Tables
Chairs
Stage
Linens
Washrooms
Power
Lighting
Staff
Event Manager
Assitants
Parking

## Timelines
4 - 6 Months Prior to Event
Choose your Event
Choose a Date
Establish your budget
Find key speakers and entertainment
Choose Event Manager
Find a location
Name and Brand your event
Choose your Theme
Build your Team
Create Your Adrvertising Plan
Create Facebook Event
Create Webstie page
3 - 4 Months Prior to Event
Start Advertising Campaign
Assign Staff roles
Assign Voluteers roles
Book entertainment: Event Emcee, DJ, Band, Speakers
Find caterer , food truck or plan food and beverage
Source out other event requirments, power, water, washrooms
Source out rentals items - tables, chairs, linens, etc
Source out theme décor
Invite non-profit oraganizations to your event
Check for any required permits
Bopk any travel requirments
Plan event timeline
Obtain Event insurance if required
1-2 Months Prior to Event
Hold contests to promote event
Send out press release to local media
Obtain any required permits
Design floor plan for Event
2-3 weeks Prior to Event
Finalize details with location
Finalize details with Entertainment
Finalize details with Rentals
Finalize Décor plan
1 Week Prior to Event
Send directions and Confirm with all vendors
Send directions and Confirm with participants
Send directions and Confirm with Staff
Close registration for event
Finalize timeline for event
Conifrm with any deliveries
Day Prior to Event
Begin set up for event
Day of Event
Meet with Staff and Volunteers and debrief